## Ark1
Lofthus frukt og saft |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6
Start Date: xx/xx/2020 |  |  | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU | M | T | W | TH | F | SA | SU
PLANNING |  | 5 d
Gather information | Content Specialist | 3 d | bar: WEEK 1 M to WEEK 1 W
Sitemap and Wireframe | UI/UX Designer | 3 d | bar: WEEK 1 W to WEEK 1 F
DESIGN |  | 14 d
Graphic Design, ID element | Graphic Designer | 6 d | bar: WEEK 1 TH to WEEK 1 SA; WEEK 2 M to WEEK 2 T; WEEK 3 T
Page Layout |  | 3 d | bar: WEEK 2 TH to WEEK 2 F; WEEK 3 T
MEETING |  | 1 d
Meeting with customer (present layout, art and talk about content) |  | 1 d | bar: WEEK 3 M
CONTENT |  | 8 d
Content writing | Content Specialist | 4 d | bar: WEEK 3 T to WEEK 3 F
Get content ready for migration | Content Specialist | 2 d | bar: WEEK 4 M to WEEK 4 T
CODING |  | 9 d
Build website | Coder (me) | 4 d | bar: WEEK 4 W to WEEK 4 SA
Add special features and interactivity | Coder (me) | 3 d | bar: WEEK 5 M to WEEK 5 W
SEO | Coder (me) | 2 d | bar: WEEK 5 TH to WEEK 5 F
MEETING |  | 1 d
Presentation of high fidelity website to Customer |  | 1 d | bar: WEEK 6 M